## Read me
HelpDesk165 — Calculation Appendix
CMPE 165 Project 1. Every number in the written report and the class deck is produced by the scripts in analysis/ and reproduced here. Shaded cells are live Excel formulas, not pasted values.
Organization | SJSU Campus Technology Services (CTS)
Product | HelpDesk165
Recommendation | GO WITH CONDITIONS
Regenerate everything | python -m analysis.run_all
Rebuild this workbook | python -m tools.build_workbook
Run the test suite | python -m pytest -q
Run the prototype | streamlit run app/Home.py
Sheet | What it contains
Assumptions | Every input, with the reasoning behind it
Part C Scoring | Weighted scoring model, Project A vs Project B
Part D NPV | Four-year discounted cash flow and NPV
Part H Risks | Risk register with qualitative score and dollar exposure
Part I Decision Tree | Three funding options and their expected values
Part J Inputs | Monte Carlo distributions for six uncertain variables
Part J Results | Simulated cost and NPV, percentiles, and thresholds
Part J Sensitivity | Which uncertainty actually moves the business case

## Assumptions
Assumptions
These are the only inputs. Everything else in this workbook is derived from them. Source: analysis/assumptions.py.
Input | Value | Unit | Basis
Annual ticket volume | 24000 | tickets/year | About 2,000 requests a month across the shared inbox, three departmental spreadsheets, and walk-ups.
Ticket volume growth | 5% | per year | Additional departments onboarded after launch.
Blended support labor rate | 32 | $/hour | Tier 1 student assistants near $22 loaded and Tier 2 staff near $48 loaded, weighted by ticket mix.
Minutes saved per ticket | 10 | minutes | Six minutes of screenshot back-and-forth removed by structured intake, plus four minutes of manual triage removed by routing.
Tool consolidation savings | 12000 | $/year | Three departmental trackers retired.
Engineering effort | 38 | person-weeks | Bottom-up estimate for the production build: SSO, real database, roster sync, reporting, accessibility, hardening.
Hours per person-week | 40 | hours | Standard.
Blended build rate | 88 | $/hour | Loaded cost of the delivery team.
SSO and roster integration | 12000 | $ one-time | Okta/Duo plus the Banner roster sync.
Security and accessibility review | 8000 | $ one-time | Required before any campus launch.
Infrastructure setup | 4000 | $ one-time | Managed Postgres, CI, monitoring.
Annual run cost | 26000 | $/year | Hosting, monitoring, and about 0.25 FTE of maintenance.
Approved capital budget | 185000 | $ | What the CTS Director can approve without a supplemental request.
Discount rate | 8% | per year | The university's stated hurdle rate for internal IT investments.
Analysis horizon | 4 | years | Assignment minimum.
Pilot cost | 46000 | $ | Eight-week paid pilot in two support categories.
Monte Carlo trials | 10000 | trials | Assignment minimum is 1,000.
Random seed | 165 |  | Makes every figure reproducible.
Adoption ramp (share of volume in the tool)
Year 1 | 55%
Year 2 | 90%
Year 3 | 100%
Year 4 | 100%

## Part C Scoring
Part C — Weighted Scoring Model
Weights total 100 percent. Scores are 1-10. The weighted columns are live formulas: weight x score.
Criterion | Weight | A score | A weighted | B score | B weighted | Why this criterion carries this weight
Strategic alignment | 25% | 9 |  | 6 |  | How directly the project advances the CTS goal of measurable service quality. Weighted highest because the division is funded against that goal.
Expected financial return | 20% | 8 |  | 7 |  | Four-year NPV and the size of the recurring saving.
Time to first value | 15% | 9 |  | 5 |  | How quickly a usable slice reaches real users. The division needs a win inside one academic year.
Delivery and technical risk | 15% | 7 |  | 6 |  | Scored inversely: a higher score means lower risk.
Stakeholder demand and sponsorship | 15% | 9 |  | 6 |  | Strength of the pull from departments and the presence of an executive sponsor.
Staffing feasibility | 10% | 8 |  | 5 |  | Whether the current team can build it without new headcount.
TOTAL
Project A | Project A — HelpDesk165 ticketing and SLA reporting
Project B | Project B — Campus room and equipment booking portal
Margin
Decision | Fund Project A — HelpDesk165 ticketing and SLA reporting
Sensitivity: no single criterion weight between 0 and 100 percent reverses this result. See analysis/weighted_scoring.py.

## Part D NPV
Part D — Net Present Value
NPV = -C0 + sum over t of Bt / (1 + r)^t. Discount factors, present values, and the NPV total are live formulas.
Discount rate (r) | 8%
Initial development cost (C0) | 157760
Year | Ticket volume | Adoption | Labor savings | Tool savings | Gross benefit | Run cost | Net cash flow | Discount factor | Present value
1 | 24000 | 55% | 70400 | 6600 |  | -26000
2 | 25200 | 90% | 120960 | 10800 |  | -26000
3 | 26460 | 100% | 141120 | 12000 |  | -26000
4 | 27783 | 100% | 148176 | 12000 |  | -26000
Sum of present values
Less initial cost
NET PRESENT VALUE
ROI on invested capital
IRR | 44.91%
Simple payback | Year 3
Discounted payback | Year 3
Benefits are scaled by the adoption ramp because a tool nobody uses saves nothing. The run cost is charged in full from year one because hosting does not wait for adoption. Part J shows why this positive NPV is not sufficient grounds to fund the full build.

## Part H Risks
Part H — Risk Register
Two scores per risk. Probability x Impact on a 1-5 scale drives the heat map; probability x dollar impact drives the budget. Ranked on exposure.
ID | Category | Risk | P (1-5) | I (1-5) | P x I | Band | Probability | Dollar impact | Exposure | Early warning trigger
R3 | Organizational / Adoption | Departments keep using the shared inbox and spreadsheets, so the labor savings that justify the whole business case never materialize. | 3 | 5 |  | Critical | 30% | 95000 |  | Fewer than 60 percent of a pilot department's requests arrive through the tool after four weeks.
R2 | Schedule / Cost | Engineering effort is underestimated, pushing the build past the spring registration change freeze and over the approved capital budget. | 5 | 4 |  | Critical | 45% | 42000 |  | Two consecutive sprints close below 70 percent of committed points.
R5 | Security / Compliance | Ticket descriptions contain FERPA-protected student information while the prototype has no access control, creating a disclosure exposure and a failed pre-launch security review. | 3 | 5 |  | Critical | 25% | 60000 |  | Any ticket body containing a student ID is readable by an account without a demonstrated need to know.
R7 | Scope | Stakeholders demand a knowledge base, live chat, and a native mobile app before they will approve launch. | 4 | 3 |  | High | 45% | 30000 |  | More than three new must-have features are added in a single steering committee meeting.
R1 | Technical | Okta/Duo single sign-on and the Banner roster sync take substantially longer than estimated because campus identity APIs are undocumented. | 4 | 4 |  | Critical | 35% | 34000 |  | Integration spike runs past its two-week timebox without a working token exchange.
R4 | People / Key person | Only one engineer understands the SLA and reporting logic, so any absence stops that work entirely. | 3 | 4 |  | High | 30% | 22000 |  | More than 60 percent of commits to the SLA and reporting modules come from a single author.
R8 | Quality | SLA and breach calculations go untested, management catches an incorrect number in a service review, and trust in the reporting is lost. | 3 | 4 |  | High | 30% | 20000 |  | A stakeholder disputes a dashboard figure that the team cannot trace back to individual tickets.
R9 | Operational / Architecture | The prototype's single-file SQLite database does not survive concurrent campus-wide use and has to be migrated mid-project. | 3 | 3 |  | Moderate | 30% | 16000 |  | Database lock errors appear in logs once more than about 20 agents work the queue at once.
R6 | External / Vendor | Canvas and Banner API changes during the summer upgrade window break the roster and course sync. | 2 | 4 |  | Moderate | 20% | 18000 |  | Vendor release notes announce a breaking change to an endpoint the integration depends on.
Total expected exposure
Part K — response for the three highest exposures
ID | Strategy | Mitigation | Contingency | Early warning
R3 | Mitigate, then transfer the decision to a gate | Do not build campus-wide first. Run the eight-week paid pilot in Classroom Technology and Canvas support, close the shared inbox for those two categories so the tool is the only intake path, and publish the SLA dashboard to the department's own leadership so they see the benefit in their own numbers. Name a department champion who is accountable for intake share, not the project team. | If intake share is still under 60 percent at week four, stop feature work and spend the remaining pilot weeks on the adoption blocker instead. If it is still under 60 percent at week eight, invoke the decision-tree stop branch: the full build is not funded and CTS loses the pilot cost rather than the build cost. | Weekly intake share for the pilot categories, measured as tickets created in HelpDesk165 divided by total requests including those still arriving by email and walk-up.
R2 | Mitigate through scope control and reserve sizing | Budget to the simulation's 80th-percentile cost rather than the point estimate, timebox the SSO integration spike to two weeks, and fix the launch scope in writing at the four features the pilot validated. Track sprint velocity from sprint one so the trend is visible before it becomes a slip. | Hold a pre-approved contingency drawdown the CTS director can release without a new funding request. If velocity misses twice, cut the roster-sync integration to a nightly CSV import, which the team estimated at one week instead of five. | Two consecutive sprints closing below 70 percent of committed points, or the integration spike passing its timebox without a working token exchange.
R5 | Avoid the exposure rather than manage it | Treat FERPA as a design constraint, not a launch checklist item. Ship role-based access control before the pilot handles a single real ticket, restrict ticket visibility to the requester plus assigned agents, and put a standing notice on the intake form telling requesters not to paste student IDs or grades. Book the campus security review at project start instead of before launch. | If the security review finds a defect, the pilot pauses and the affected tickets are purged and re-created without the sensitive field. A documented incident-response path to the campus privacy officer exists before the pilot opens, not after an incident. | Any automated scan hit for a nine-digit student ID pattern in a ticket body, or any access-log entry showing a ticket read by an account that is neither the requester nor the assignee.

## Part I Decision Tree
Part I — Decision Tree and Expected Monetary Value
Decision: How should CTS fund the production version of HelpDesk165: build it outright now, license a commercial IT service-management product, or fund a small paid pilot first and decide afterwards? EMV = sum of probability x value. The contribution and EMV columns are live formulas.
Decision | Outcome | Probability | Net value (4 yr) | P x value | Branch EMV | Reasoning
Build the full product now | Campus-wide adoption takes hold | 60% | 205000 |  |  | Four-year net value if departments move their intake onto the tool and the labor savings land as modeled.
Build the full product now | Adoption stalls at a few departments | 40% | -95000 |  |  | The build is paid for but most volume stays in the shared inbox, so only a fraction of the savings is realized.
License a commercial ITSM product | Product fits campus processes as sold | 55% | 120000 |  |  | Savings arrive quickly but recurring license fees consume most of them.
License a commercial ITSM product | Heavy customization is required | 45% | 15000 |  |  | Consultants and workflow rework erode almost all of the benefit.
Fund an eight-week paid pilot, then decide | Pilot validates demand, then build | 65% | 176000 |  |  | Same build as option one, minus the pilot spend and one quarter of delayed benefit, but with adoption de-risked.
Fund an eight-week paid pilot, then decide | Pilot does not validate demand, stop | 35% | -46000 |  |  | The pilot cost is lost, but the full build is never funded.
Comparison
Option | EMV | Best case | Worst case | P(loss)
Fund an eight-week paid pilot, then decide |  | 176000 | -46000 | 35%
Build the full product now |  | 205000 | -95000 | 40%
License a commercial ITSM product |  | 120000 | 15000 | 0%
Decision | Fund an eight-week paid pilot, then decide — highest EMV at $98,300, $13,300 ahead of Build the full product now, and it caps the downside at $46,000 instead of $95,000.

## Part J Inputs
Part J — Monte Carlo Input Distributions
10,000 trials, seed 165. Six uncertain variables; the assignment asks for at least three.
Variable | Distribution | Parameters | Sampled mean
Engineering effort (person-weeks) | Triangular | min 30, likely 38, max 62 | 43.35
Blended loaded build rate ($/hr) | Normal, clipped | mean 88, sd 7, clipped to [70, 118] | 88.08
SSO / Banner rework cost ($) | Bernoulli x Triangular | p 35%, then triangular 8,000 / 15,000 / 34,000 | 6683.34
Minutes saved per ticket | Triangular | min 4, likely 10, max 14 | 9.31
Steady-state adoption share | Triangular | min 55%, likely 92%, max 100% | 0.8242
Annual run cost ($) | Uniform | 20,000 to 34,000 | 26989.72
Effort is triangular and right-skewed because software effort overruns far more often than it underruns. That asymmetry is the reason the simulated mean cost exceeds the team's point estimate.

## Part J Results
Part J — Simulation Results
The deterministic figures in Part D use the mode of every input. These are the distributions those single values were hiding.
Build cost
Team point estimate (Part D) | 157760
Simulated mean | 183414.2
Median (P50) | 180823.1
Low case (P10) | 148459.41
P80 — recommended budget | 208010.76
High case (P90) | 222741.62
Optimism gap (mean minus estimate) | 25654.2
Approved capital budget | 185000
P(cost exceeds approved budget) | 44.08%
Four-year NPV
Deterministic NPV (Part D) | 179669.77
Simulated mean | 54286.13
Median (P50) | 54331.58
Worst case (P5) | -81196.11
Low case (P10) | -56353.91
High case (P90) | 164775.29
Best case (P95) | 191975.8
P(NPV below zero) | 27.3%
Percentile | Total build cost | Four-year NPV
P5 | 140992.5 | -81196.11
P10 | 148459.41 | -56353.91
P25 | 161826.37 | -6261.99
P50 | 180823.1 | 54331.58
P75 | 202360.96 | 113532.3
P80 | 208010.76 | 127847.35
P90 | 222741.62 | 164775.29
P95 | 234739.88 | 191975.8
Decision this changes: hold capital against the P80 cost, not the point estimate, and spend $46,000 on a pilot to measure the two variables that dominate NPV before committing the rest.

## Part J Sensitivity
Part J — Sensitivity
Correlation of each sampled input with the resulting NPV. The square of the correlation is roughly the share of NPV variance it explains.
Variable | Correlation with NPV | Share of NPV variance
minutes saved | 0.7928
steady adoption | 0.4776
effort person weeks | -0.2781
annual run cost | -0.1758
build rate | -0.1524
sso rework cost | -0.1334
Minutes saved per ticket and adoption dominate. Engineering effort, the variable teams normally pad, is third. CTS is buying a behavior change more than a software project, which is exactly what a pilot can test cheaply.